## READ ME
Options to Choose for Environmental Compliance documents | Column3 | Definition
Unsure |  | Unsure of how environmental compliance will be satisfied
CEQA satisfied by completed NEPA |  | Using a statutory exemption, CAL FIRE will be the lead agency to file a CEQA NOE after grantee furnishes a completed NEPA document, per AB 211 (previously SB 901).
CEQA Mitigated Negative Declaration (MND) |  | Environmental compliance will be satisfied with an existing or new CEQA document. This may include filing a Notice of Exemption NOE for a statutory or categorical exemption to CEQA.
CEQA Negative Declaration (ND) |  | Environmental compliance will be satisfied with an existing or new CEQA document. This may include filing a Notice of Exemption NOE for a statutory or categorical exemption to CEQA.
CEQA Notice of Categorical Exemption (CE-DN/NOE) |  | Environmental compliance will be satisfied with an existing or new CEQA document. This may include filing a Notice of Exemption NOE for a statutory or categorical exemption to CEQA.
CEQA Notice of Statutory Exemption (SE-DN/NOE) |  | Environmental compliance will be satisfied with an existing or new CEQA document. This may include filing a Notice of Exemption NOE for a statutory or categorical exemption to CEQA. CAL FIRE Sacramento HQ may be lead agency.
CEQA Environmental Impact Report (EIR) |  | Environmental compliance will be satisfied with an existing or new CEQA document. This may include filing a Notice of Exemption NOE for a statutory or categorical exemption to CEQA.
CAL FIRE ERRF (in conjuction with NOE) |  | CAL FIRE Sacramento HQ may be lead agency.
CAL FIRE VTP Project Specific Analysis (PSA) |  | CAL FIRE Sac HQ is NOT lead agency. Local unit will work with grantee.
CAL FIRE VMP Project Plan (VMP) |  | CAL FIRE Sac HQ is NOT lead agency. Local unit will work with grantee.
Timber Harvest Plan |  | CEQA environmental compliance will be satisfied using a THP document. Note, this is only appropriate for commercial timber operations.
Other |  | Some other specific environmental compliance
CAL FIRE Tribal Wildfire Resilience Grants
Project Workbook
Treatment Acres
The Treatment Acres worksheet must specify the treatment areas, ownership type, and funds to be spent by treatment. List only one ownership type and only one treatment type per row. All treatment areas must be included and a treatment area may need to be listed more than once.
Environmental Compliance
List all the treatment areas and treatments proposed to be funded under the grant in the Environmental Compliance worksheet. Identify the environmental compliance document that have been "completed and filed" or "not completed and filed." The documents that have been completed and filed should be submitted with the grant application. All environmental permitting must be completed within one year of the grant agreement start date.
Email enviromental compliance questions to tribalwildfireresilience@fire.ca.gov and cegrants.ceqa@fire.ca.gov
Deliverables List the goals and objectives of a successful project. Be as specific as possible.
Treatment Options Details to help complete the Treatment Acres tab. Defines and displays Treatment Objective and Treatment Activity Options

## Deliverables
CAL FIRE Tribal Wildifre Resilience Grants Program
Purpose | Outcomes (Things You Plan to Achieve), Up to 12 please | When?
1. Paid on time & reporting up to date! | Project invoicing & reporting. Includes acres treated & deliverable updates | Quarterly
| Hiring admin personnel to help with grant project management | Starts Fall 2025.
2. Community outreach | Publication and sharing of defensible space materials for Tribal members. | Starts Spring 2026
| Community meetings on treatments. 3 yearly forums for feedback from Tribal members and 3 yearly separate meetings for neighbors. | Annually, springtime
3. Formation of youth crew | Research other Tribal Youth Crew programs, establish guidelines of youth crew with internal departments, and publish outreach materials. | Fall 2025
| Recruit and onboard 12 Tribal youth members to a stipend-paid seasonal position. | Spring 2026
| Train crew and achieve certifications (Red Card, Chainsaw, First Aid) to prepare for implementation work. | Training twice a year seasonally.
4. Stewardship Plan | RFP for forestry contractors to assist in writing plan and hiring of an internal position (Tribal Forester) to increase capacity of Tribe. | Winter 25-2026
| Complete biological and cultural resource surveys. Draft environmental compliance (CEQA Notice of Exemption). Complete enviornmental compliance process. | Ongoing, completed by end of grant.
| Request input and pay stipend to Tribal elders and cultural practitioners who are not employees for their time and consideration in formation of the Stewardship Plan. | Ongoing, completed by end of grant.

## Treatment Acres
| Project type: | Implementation: field treatment acres --> Fill out table below.
| TOTAL UNIQUE FOOTPRINT ACRES IN PROPOSED PROJECT= | 187 |  |  | GRANT FUNDS COST PER ACRE= |  | 1473.262 |  | TOTAL COST PER ACRE= | 1687.1658
|  | (enter value above) |  |  |  |  | (auto calculated) |  |  | (auto calculated)
(auto calculated)
Treatment Number | Treatment Area Name | Ownership Type | Jurisdiction | Treatment Objective | Treatment Activity | Activity Description (Optional) | Proposed Acres To Be Treated | Broad Vegetation Type | Estimated Grant Funds | Estimated Matching Funds | Estimated Activity Total Cost per Acre | Total Cost | Notes (Optional)
A | Example Area 1 | Forest Service | FRA | Reforestation | Tree Planting (Manual) |  | 1000 | Timber | 350000 | 0 | 350 | 350000
B | Example Area 2 | Tribal - Fee Title | LRA | Fuels_Reduction | Ecosystem-Specific Tending Activity | Oak & acorn restoration: hand thin and pile for fuel reduction & to remove competing vegetation | 50 | Timber | 100000 | 25000 | 2500 | 125000
C | Example Area 2 | Tribal - Trust Land | FRA | Tribal_Land_Management | Ecosystem-Specific Tending Activity (please describe) |  | 50 | Timber | 50000 | 25000 | 1500 | 75000
D | Example Area 3 | Private (non-industrial) | SRA | Fuels_Reduction | Other |  | 50 | Timber | 100000 | 25000 | 2500 | 125000
A | Cow Corner | Tribal - Allotments (Trust) | FRA | Fuels_Reduction | Fuel Break (Shaded) |  | 50 | Timber | 100000 | 0 | 2000 | 100000 | Dense overgrowth makes allotments more expensive per acre than the fee title land, but they are very high priority to take care of
B | Berry Point | Tribal - Fee Title | SRA | Fuels_Reduction | Fuel Break (Shaded) |  | 62 | Timber | 93000 | 0 | 1500 | 93000
C | Berry Point | Tribal - Fee Title | SRA | Tribal_Land_Management | Planting Native Species (please describe) | Planting for basketry | 1 | Grass | 10000 | 0 | 10000 | 10000
D | Campground | Private (non-industrial) | LRA | Pest_Management | Invasive Plant Removal | This area traditionally maintened with cultural fire | 30 | Timber | 10000 | 20000 | 1000 | 30000 | Campground providing match to support project
E | Truck Trail | Special District | SRA | Fuels_Reduction | Fuel Break (Not Shaded) |  | 15 | Brush | 22500 | 0 | 1500 | 22500 | Local Water District
F | Reservation Trail | Tribal - Trust Land | FRA | Prescribed_Fire | Site Preparation |  | 10 | Timber | 10000 | 10000 | 2000 | 20000 | BIA fuels and fire crews will assist with rx burn
G | Reservation Trail | Tribal - Trust Land | FRA | Prescribed_Fire | Broadcast Burning |  | 10 | Timber | 5000 | 10000 | 1500 | 15000 | BIA fuels and fire crews will assist with rx burn
H | Reservation Trail | Tribal - Trust Land | FRA | Fuels_Reduction | Invasive Plant Removal |  | 20 | Timber | 10000 | 0 | 500 | 10000
I | Reservation Trail | Tribal - Trust Land | FRA | Tribal_Land_Management | Cultural Burning - Broadcast |  | 20 | Timber | 15000 | 0 | 750 | 15000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Sums | -- | -- | -- | -- | -- |  | 218 | -- | 275500 | 40000 | 20750 | 315500
(the sum of treated acres should be equal or greater than total unque footprint acres)
Instructions
1. Select Project Type. For planning projects with no acres treated on the ground, this worksheet will be complete, the rest of the table will be blank. Please see the "Treatment Options" worksheet for more information and definitions on Treatment Objectives, Treatment Activities, and Broad Vegetation Type while completing this woksheet.
2. For all projects with any acres treated on the ground that directly change the landscape:
  a) Enter the total number of acres treated in cell C14 (the red one). If some acres have more than one activity, they are counted only ONCE here.
  b) List all treatments.
  c) Each row should have only one ownership type, fire response jurisdiction, treatment objetive, and treatment activity. Include one objective and one activity per row. If one place has multiple treatments, they would be multiple rows. If one treatment occurs over more than one ownership, there would be a row for each ownership type.
  d) The dropdown menus have Treatment Objectives and Treatment Activities, These are listed in the treatment Options tab. If you plan to do work that these activities don't describe well, please select the closest option and describe it in COLUMN G.
CAL FIRE Tribal Wildfire Resilience
Treatment Tracking Sheet
GROUND-DISTURBING ACTIVITY INFORMATION

## Environmental Compliance
Treatment Number | Lead Agency | Document to Be Used for State Requirement | Date Filed | Document Expiration Date | Document Status | Document # | Contractor for Document Preparation | Notes (Optional) | Treatment Number | Federal Doc Req'd? | Fed. Doc. Status | State Doc. Status | Days
1 | CAL FIRE | CEQA satisfied by completed NEPA | 2018-08-18 | 2019-08-17 | In Progress | 1-22EM-00042-SAC | XYZ Forestry & Assoc |  | 1 | #REF! | #REF! | #REF! | #REF!
2 | Sacramento RCD | CEQA | 2021-06-20 |  | In Progress | 2021000123 | XYZ Forestry & Assoc |  | 2 | #REF! | #REF! | #REF! | #REF!
3 | Sacramento County | Timber Harvest Plan | 2021-06-20 |  | Completed | Pending | ABC Environmental |  | 3 | #REF! | #REF! | #REF! | #REF!
4 | BIA | Unsure | N/A | N/A | Not Started | Pending | BIA |  | 4 | #REF! | #REF! | #REF! | #REF!
1.1 | BIA | CEQA satisfied by completed NEPA | 2021-06-14 | 2027-08-05 | Completed | 504500123 | XYZ Forestry & Assoc | Environmental compliance completed for activities included in proposed project work.
2.1 | BIA | CEQA satisfied by completed NEPA | 2021-06-15 | 2027-08-06 | Completed | 1-65TM-00415-SAC | XYZ Forestry & Assoc
2.2 | BIA | CEQA satisfied by completed NEPA | 2021-06-16 | 2027-08-07 | Completed | 1-65TM-00415-SAC | XYZ Forestry & Assoc
3.1 | Sacramento RCD | Unsure | N/A |  | Not Started | Pending | Sac RCD
4.1 | State Parks | CEQA Notice of Categorical Exemption (CE-DN/NOE) | N/A |  | In Progress | Pending | State Park
4.2 | State Parks | CEQA Notice of Categorical Exemption (CE-DN/NOE) | N/A |  | In Progress | Pending | State Park
5.1 | BIA | CEQA satisfied by completed NEPA | N/A |  | In Progress | Pending | Davey Environmental
5.2 | BIA | CEQA satisfied by completed NEPA | N/A |  | In Progress | Pending | Davey Environmental
5.3 | BIA | CEQA satisfied by completed NEPA | N/A |  | In Progress | Pending | Davey Environmental
[9 empty] | 19 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 20 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 21 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 22 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 23 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 24 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 25 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 26 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 27 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 28 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 29 | #REF! | #REF! | #REF! | #REF!
[9 empty] | 30 | #REF! | #REF! | #REF! | #REF!
CAL FIRE Tribal Wildfire Resilience Program
Environmental Compliance Sheet
Instructions:
Enter the Treatment Component Number (TCN) as listed on the Treatment Acres Sheet. Complete the pink highlighted cells for each treatment number.

## Treatment Options
CAL FIRE Tribal Wildfire Resilience Program Diagram of Relationships between Treatment Objectives and Activities
CAL FIRE Tribal Wildfire Resilience Program Definitions of Treatment Objectives
Biomass Utilization
Work conducted in an area where the primary objective is to utilize woody biomass for wood products, and/or generate energy through combustion or gasification, and/or utilize woody biomass to help develop markets for beneficial uses of the material.
Fuels Reduction
Work conducted in an area where the primary objective is to reduce fuel loads. Work should be focused on treating understory trees and brush with the goals of reducing fire hazards, improving tree growth, stabilizing carbon in retained trees, and increasing forest resilience.
Pest Management
Work conducted in an area where the primary objective is to address pest control and related forest health improvement, while reducing pest-related mortality, improving tree growth and vigor, stabilizing carbon retained in trees, and increasing forest resilience.
Prescribed Burning
Work conducted in an area where the primary objective is to reintroduce fire to fire-adapted forest ecosystems. The work may serve multiple purposes, including reducing fuel loads; creating heterogenous and diverse vegetation; maintaining ancestral practices of indigenous communities; and/or promoting healthy ecosystem processes (e.g., water storage, pest resistance).
Reforestation
Work conducted to promote the reforestation of understocked forestland and areas burned by wildfire to increase carbon sequestration and rebuild natural habitats and ecosystems. Planting should establish a diverse, native forest, which will result in stable carbon sequestration and storage, improved watershed and habitat functions, and forest resilience.
CAL FIRE Program Tribal Wildfire Resilience Definitions of Treatment Activities
Biomass Removal (Biochar): Biomass (tree limbs, tops, and woody material) removed from the site by manual or mechanical means for use in biochar.
Biomass Removal (Electricity): Biomass (tree limbs, tops, and woody material) removed from the site by manual or mechanical means for use in electrical generation.
Biomass Removal (Heat): Biomass (tree limbs, tops, and woody material) removed from the site by manual or mechanical means for use in alternative sources of heating.
Biomass Removal (Renewable Fuels): Biomass (tree limbs, tops, and woody material) removed from the site by manual or mechanical means for use in biofuels.
Biomass Removal (Wood Products): Biomass (tree limbs, tops, and woody material) removed from the site by manual or mechanical means for use in wood products.
Broadcast Burning: Prescribed burning where fire is applied to the majority or entire area within a well-defined boundary for reduction of fuel hazard, as a resource management treatment, or both.
Chipping: Breaking, cutting, or grinding trees into wood chips and leaving on site. Note: see biomass removal activities if removing woodchips off-site.
Commercial Thinning (Tractor Yarding): Removal of trees by tractor yarding for commercial purposes (sawlogs, dimensional lumber) and to reduce stocking.
Commercial Thinning (Cable Yarding): Removal of trees by cable yarding for commercial purposes (sawlogs, dimensional lumber) and to reduce stocking.
Cultural Burning: "the intentional application of fire to land by a California Native American tribe, a tribal organization, or a cultural fire practitioner to achieve cultural goals or objectives, including for sustenance, ceremonial activities, biodiversity, or other benefits." Cal. Civ. Code § 3333.8 (a)
Demonstration Data Collection: Installation, observation, data collection and/or maintenance of demonstration project area. Ecosystem Specific Tending Activities: The intentional, prescribed modification of ecosystems to benefit California Native American tribes, tribal , tribal organizations, or cultural fire practitioners (as defined by PRC 4002.6). Includes pruning and tending activities that may be specific to each area.
Facilitated Donation: Acquisition of land by landowner donation to protect and maintain traditional forestland benefits, such as timber production, wildlife habitat, watershed protection and/or open space. Note: only use for Land Protection objective.
Fencing: Fencing to protect sensitive wildlife habitat such as wet meadow sites, riparian areas, seedling establishment site, and streams.
Fuel Break (Shaded): Removal of vegetation to create a gap in vegetation (fuels) that acts as a barrier to slow or stop the progress of wildlife. Overhead canopy is retained in a shaded fuel break.
Fuel Break (Not Shaded): Removal of vegetation to create a gap in vegetation (fuels) that acts as a barrier to slow or stop the progress of wildlife. Overhead canopy is removed in a fuel break.
Fungicide: Application of fungicide used to target and kill undesirable fungicide.
Grazing: Livestock grazing for the purposes of reducing fire fuels.
Herbicide: Application of herbicide used to target and kill undesirable plants.
Imagery Data Collection: Acres with imagery including LiDAR, sonar, high resolution aerial imagery, etc.
Insecticide: Application of insecticide used to target and kill undesirable insects.
Invasive Plant Removal: Manual removal of invasive plant species.
Lop and Scatter: Hand method of cutting limbs and tops of felled trees into smaller pieces and scattered across the site.
Mastication: Pulverizing vegetation down to ground level using a masticator.
Other: Please provide specific information including explanation of why this does not fit within the activities listed.
Piling (Manual): Hand piling of fuels.
Piling (Mechanical): Machine piling of fuels.
Pile Burning: Burning of piled material including hand and machine piles.
Planting: The establishment or re-establishment of forest cover artificially by planting seedlings and/or cuttings with or without site preparation. Planting Native Species: Planting of native vegetation in order to meet cultural objectives that may include erosion control, biodiversity, subsistence or other benefits. This is distinct from timber or oak reforestation planting, which goes in the Reforestation category.
Pruning: The removal of side branches and multiple leaders from a standing live tree.
Purchase of Fee Title: Acquisition by purchase of fee title of land to protect and maintain traditional forestland benefits, such as timber production, wildlife habitat, watershed protection and/or open space.
Purchase of Conservation Easement: Acquisition by purchase of conservation easement of land to protect and maintain traditional forestland benefits, such as timber production, wildlife habitat, watershed protection and/or open space.
Oak Woodland Restoration: Any forest management activity with the primary intent of oak woodland restoration.
Research Data Collection: Installation, observation, and/or maintenance of research area.
Removal of Diseased/Infested Trees: Cutting down trees that are infected, diseased, or susceptible to pests for the purposes of pest management.
Right of Way Clearance: Work conducted within the right of way along fire roads, county roads, or highways for purposes of improved ingress and egress. This includes the removal of dead trees resulting from insect or drought. Right of Way Clearance is not done with the intent of stopping a fire at the location of work but instead focuses on ingress and egress enhancement. Do not use if the intent is to stop a fire.
Road Removal: Removing previously constructed roads and returning to a forested state. May include grading and planting.
Site Preparation: The removal or alterations of fuels or ground material to prepare for prescribed fire or reforestation. Includes constructing piles, constructing fire line, soil ripping, etc.
Tarping: Cover and seal a wood pile with clear UV resistant plastic to prevent forest pests (Bark Beetle, GSOB, etc.) from emerging from infested wood or colonizing freshly cut wood, preferably placed in full direct sunlight.
Thinning (Manual): Manually cutting trees to reduce stocking or fuel loading, including pre-commercial thinning. If commercializing, see commercial thinning or biomass options.
Thinning (Mechanical): Mechanically cutting trees to reduce stocking or fuel loading, including pre-commercial thinning. If commercializing, see commercial thinning or biomass options.
Tree Shelters: Installation of tree shelters, which are tubes placed over seedlings to protect from deer, rabbits, or other wildlife and from sun scald.
Tree Planting (Manual): Planting of trees manually to increase stocking.
Tree Planting (Mechanical): Planting of tree mechanically to increase stocking.
CAL FIRE’s CalMAPPER Definitions of Vegetation Types
The Treatment Area worksheet solicits information about the vegetation type that characterizes the area in which ground-disturbing treatment activities occur (please see the “Broad Vegetation Type” column in the Treatment Tracking sheet). This information is entered into CAL FIRE’s CalMAPPER platform. To identify the Broad Vegetation Type, ground observation is sufficient to determine the general vegetation type in the area in which a treatment activity takes place. If multiple types are present within a treatment activity area, choose the majority vegetation type. Please refer to the following definitions.
Grass: Areas dominated by grasses or herbaceous vegetation and exhibiting tree or shrub canopy below 10%.
Brush: Areas dominated by at least 10% cover of brush also commonly referred to as shrub, scrub, or bush. These lands are dominated by woody plants but lack tree cover.
Woodland: A low-density forest forming open habitats with plenty of sunlight and limited shade. Tree species can include oaks as well as juniper, gray pine, and pinyon pine.
Timber: Areas dominated by at least 10% conifer trees. Excludes areas dominated by juniper, gray pine, and pinyon pine, which typically form open woodland habitats.

## Treatment Options Diagram (hidden)
Treatment Objective | Biomass_Utilization | Fuels_Reduction | Other | Pest_Management | Prescribed_Fire | Reforestation | Tribal_Land_Management
| Biomass Removal (Biochar) | Chipping | Other | Chipping | Broadcast Burning | Fencing | Cultural Burning - Broadcast
| Biomass Removal (Electricity) | Commercial Thinning (Cable Yarding) |  | Crushing | Other | Herbicide | Cultural Burning - Other (please describe)
| Biomass Removal (Heat) | Commercial Thinning (Tractor Yarding) |  | Fungicide | Site Preparation | Invasive Plant Removal | Ecosystem-Specific Tending Activity (please describe)
| Biomass Removal (Renewable Fuels) | Fuel Break (Not Shaded) |  | Herbicide |  | Other | Planting Native Species (please describe)
| Biomass Removal (Wood Products) | Fuel Break (Shaded) |  | Insecticide |  | Road Removal
| Other | Grazing |  | Invasive Plant Removal |  | Site Preparation
| Piling (Manual) | Herbicide |  | Other |  | Tree Planting (Manual)
| Piling (Mechanical) | Invasive Plant Removal |  | Pile Burning |  | Tree Planting (Mechanical)
|  | Lop and Scatter |  | Piling (Manual)
|  | Mastication |  | Piling (Mechanical)
|  | Oak Woodland Restoration |  | Pruning
|  | Other |  | Removal of Diseased/Infested Trees
|  | Pile Burning |  | Tarping
|  | Piling (Manual) |  | Thinning (Manual)
|  | Piling (Mechanical) |  | Thinning (Mechanical)
Pruning
Right of Way Clearance
Thinning (Manual)
Thinning (Mechanical)
Treatment Activity

## Menus (hidden)
OwnershipType | Objectives | Fuels_Reduction | Prescribed_Fire | Pest_Management | Reforestation | Biomass_Utilization | Research | Forest_Conservation | Tribal_Land_Management | Other | NEPA/CEQA Status | RA Type | Quarter endings | Yes/No | Setbacks/challenges | EC Status | Months | Years | StateDocs | FederalDocs | ProjectGeneratedIncome | TreatmentActivityLookup | CalMAPPERActivity | YesList | NoList | YesNoList | VerificationMethod | ApprovalStatus | Project Type | Ground Disturbing Work
Bureau of Land Management | Biomass_Utilization | Chipping | Broadcast Burning | Chipping | Fencing | Biomass Removal (Biochar) | Data Collection | Facilitated Donation | Cultural Burning - Broadcast | Other | Completed | FRA | 2021-06-01 | Yes | COVID 19 - Travel restrictions | Not started | January | 2021 | CAL FIRE ERRF (in conjunction with NOE) | Decision Notice - Finding of No Significance (DN-FONSI) | Interest earned on advance | Fuels_Reduction Oak Woodland Restoration | Fuels Reduction, Thinning (Manual or Mechanical) | Yes | NA | YesList | Observation on-site in the field | Approved | Implementation | Implementation: field treatment acres --> Fill out table below.
Bureau of Land Management (wilderness) | Fuels_Reduction | Commercial Thinning (Cable Yarding) | Other | Crushing | Herbicide | Biomass Removal (Electricity) | Data Collection | Other | Cultural Burning - Other (please describe) |  | In Progress | LRA | 2021-09-01 | No | COVID-19 - Constraints in budget/hiring | In Progress | February | 2022 | CAL FIRE Exemption/Emergency Harvest Document | Environmental Assessment (EA) | Revenue from biomass sales | Fuels_Reduction Right of Way Clearance | Fuels Reduction, Thinning (Manual or Mechanical) | No |  | NoList | Drone imagery | Needs follow-up | Planning | Planning: does NOT have any acres treated on the ground --> Leave table below blank.
Department of Defense | Other | Commercial Thinning (Tractor Yarding) | Site Preparation | Fungicide | Invasive Plant Removal | Biomass Removal (Heat) | Demonstration | Purchase Conservation Easement | Ecosystem-Specific Tending Activity (please describe) |  | N/A | SRA | 2021-12-01 |  | COVID-19 - Personnel kept out of field for safety measures | Complete | March | 2023 | CAL FIRE VMP Project Plan (VMP) | Environmental Impact Statement (EIS) | Other | Prescribed_Fire Pile Burning | Broadcast Burn, Pile Burning |  |  |  | Other |  |  | Planning: does have acres treated on the ground. --> Fill out table below.
Forest Service | Pest_Management | Fuel Break (Not Shaded) |  | Herbicide | Other | Biomass Removal (Renewable Fuels) | Imagery Data Collection | Purchase Fee Title | Planting Native Species (please describe) |  |  |  | 2022-03-01 | Yes/No/NA | Delay in receiving match funding | NA | April | 2024 | CAL VTP Project Specific Analysis (PSA) | Final Environmental Assessment (FEA) |  | Prescribed_Fire Oak Woodland Restoration | Broadcast Burn, Broadcast Burning |  |  |  |  | ResetStatus
Forest Service (wilderness) | Prescribed_Fire | Fuel Break (Shaded) |  | Insecticide | Road Removal | Biomass Removal (Wood Products) | Other | [5 empty] | 2022-06-01 | Yes | Difficulty in collecting necessary environmental compliance documentation | Basic Status | May | 2025 | CDFW Streambed/Lake and Streambed Alteration Agreement (SAA/LSA or "1600") | Final Environmental Impact Statement (FEIS) |  | Reforestation Fencing | Reforestation, Site Preparation |  |  |  |  | Reset
Local Government | Reforestation | Grazing |  | Invasive Plant Removal | Site Preparation | Other | Research | [5 empty] | 2022-09-01 | No | Difficulty in obtaining insurance for prescribed burning | In progress | June | 2026 | CEQA Environmental Impact Report (EIR) | Initial Study (IS) |  | Reforestation Oak Woodland Restoration | Reforestation, Tree Planting (Manual or Mechanical) |  |  |  |  | Approved
National Park | Tribal_Land_Management | Herbicide |  | Other | Tree Planting (Manual) | Piling (Manual) | [6 empty] | 2022-12-01 | NA | Fire in project scope - Damage (but not necessarily high-severity fire) | Complete | July | 2027 | CEQA Mitigated Negative Declaration (MND) | Other |  | Reforestation Road Removal | Reforestation, Site Preparation |  |  |  |  | Needs follow-up
National Park (wilderness) |  | Invasive Plant Removal |  | Pile Burning | Tree Planting (Mechanical) | Piling (Mechanical) | [6 empty] | 2023-03-01 |  | Fire in project scope - Significant damage (high-severity fire) |  | August | 2028 | CEQA Negative Declaration (ND) | Record of Decision (ROD) |  | Reforestation Tree Shelters | Reforestation, Site Preparation
Other |  | Lop and Scatter |  | Piling (Manual) | [8 empty] | 2023-06-01 | Yes | Fire in project vicinity - Capacity/financial resources diverted |  | September | 2029 | CEQA Notice of Categorical Exemption (CE-DN/NOE)
Other Federal |  | Mastication |  | Piling (Mechanical) | [8 empty] | 2023-09-01 | Yes | Fire in project vicinity - No/delayed access |  | October | 2030 | CEQA Notice of Statutory Exemption (SE-DN/NOE)
Other State |  | Oak Woodland Restoration |  | Pruning | [8 empty] | 2023-12-01 |  | Lack of/difficulty in recruiting qualified personnel |  | November | 2031 | Coastal Development Permit
Private (industrial forestry) |  | Other |  | Removal of Diseased/Infested Trees | [8 empty] | 2024-03-01 |  | Legal challenges raised by potential/current litigants |  | December |  | Initial Study (IS)
Private (non-industrial) |  | Pile Burning |  | Tarping | [8 empty] | 2024-06-01 |  | No/late authorization for prescribed burn - Area resources for wildfire incident response were too low |  |  |  | Other
Special District |  | Piling (Manual) |  | Thinning (Manual) | [8 empty] | 2024-09-01 |  | Other |  |  |  | SB 901
State Demonstration Forest |  | Piling (Mechanical) |  | Thinning (Mechanical) | [8 empty] | 2024-12-01 |  | Subcontractor - Delays not related to fire in project vicinity |  |  |  | Timber Harvest Plan (THP)
State Park |  | Pruning | [10 empty] | 2025-03-01 |  | Subcontractor - Other issues
Tribal - Allotments (Trust) |  | Right of Way Clearance | [12 empty] | Topographic (high-incline)/road access constraints
Tribal - Fee Title |  | Thinning (Manual) | [12 empty] | Unexpected volume of low-priced competing biomass on market
Tribal - Other |  | Thinning (Mechanical) | [12 empty] | Weather - Conditions too hot to begin ignitions
Tribal - Trust Land | [14 empty] | Weather - Conditions too wet to begin ignitions
University | [12 empty] | LiquidationDates |  | Weather - Conditions too windy to begin ignitions
2022-06-30
2023-06-30
2024-06-30
2025-06-30
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Truck Trail
Reservation Trail
Reservation Trail
Reservation Trail
Reservation Trail

## Chart (hidden)
Treatment Objective | Activity Acreage To Be Treated | Activity Acreage Treated
Fuels_Reduction | 147 | #REF!
Prescribed_Fire | 20 | #REF!
Pest_Management | 30 | #REF!
Reforestation | 0 | #REF!
Biomass_Utilization | 0 | #REF!
Research | 0 | #REF!
Forest_Conservation | 0 | #REF!
Other | 0 | #REF!